🚀 GROWTH & TRAFFIC PLAN

OutAtlas + Travel in Pride | March 28 – August 4, 2026

## EXECUTIVE SUMMARY

Brand-new app launch + brand-new social channels. Zero paid budget ($100/month maximum).

Massive opportunity window: Amsterdam Pride (July 22–Aug 4) is the strategic anchor.

Strategy: Heavy emphasis on organic social momentum, partnership leverage, community engagement, and SEO.

Timeline: 16 weeks to Amsterdam Pride. Phase 1 (Now–May): Foundation. Phase 2 (June): Positioning. Phase 3 (July–Aug): Peak campaign.

## 📱 ORGANIC SOCIAL STRATEGY

## TikTok (Primary Driver for Reach)

Why: TikTok's algorithm favors authentic, niche content. LGBTQ+ travelers are huge. Short-form video showcases app features, Pride moments, and travel tips.

Posting cadence: 3–4 TikToks per week

Expected performance: 1.5–3% CTR. Aim for 1 TikTok to hit 10k–50k views within 2 months.

## ⚡ PRIORITIZED ACTION LIST

## 🔴 DO THIS WEEK (Foundation)

| Task | Category | Status |
| --- | --- | --- |
| Install Meta Pixel on website | Web Dev | ⬜ |
| Install TikTok Pixel on website | Web Dev | ⬜ |
| Install Google Tag Manager + conversion tracking | Web Dev | ⬜ |
| Identify 30 micro-influencers (10k–50k followers) | Partnerships | ⬜ |
| Create Pinterest account + brand boards | Social | ⬜ |
| Apply for IGLTA membership | Admin | ⬜ |
| Outline first 3 blog posts | Content | ⬜ |
| Research Grindr/Scruff media kits | Partnerships | ⬜ |

## 📊 EXPECTED KPIs & BENCHMARKS (By Amsterdam Pride)

| Metric | Baseline | Target (Aug 4) |
| --- | --- | --- |
| Website monthly visitors | 0 | 5k–8k |
| TikTok followers | 0 | 500–2k |
| Instagram followers | 0 | 200–500 |
| YouTube subscribers | 0 | 100–300 |
| Pinterest followers | 0 | 200–500 |
| App downloads | 0 | 2k–5k |
| Email list size | 0 | 1k–2k |
| Cost per download | – | $15–25 |
| Brand media mentions | 0 | 1–3 |

## 💰 BUDGET ALLOCATION ($100/month × 4 months = $400 total)

| Channel | Monthly | Notes |
| --- | --- | --- |
| TikTok retargeting ads | $10 | Warm audience |
| Meta Reels retargeting ads | $10 | Warm audience |
| Google Search retargeting | $10 | High intent |
| Grindr/Scruff test ads | $30 | Niche, high-value (June–July) |
| Tools (Canva, Buffer, scheduling) | $30 | Design + social |
| Miscellaneous (posters, guerrilla) | $10 | Offline tactics |

Note: Paid budget ($60/month) is intentionally lean. Organic growth will drive 80%+ of your growth through organic social, SEO, and partnerships.